## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US1 | Create Applicant Profile | As a TA applicant, I want to create my applicant profile, so that I can provide my personal information for job applications. | Must | 3 | 1. The TA applicant can enter basic personal information. 2. The TA applicant can enter skills and availability. 3. The system can save the applicant profile. 4. The system shows a prompt when required information is missing. | 5 | Supports applicants in entering and saving basic information. | 2026-04-19 | 2026-05-03
US2 | Upload CV | As a TA applicant, I want to upload my CV, so that module organisers can review my qualifications. | Must | 1 | 1. The TA applicant can upload a CV. 2. The CV can be linked to the applicant profile. 3. The system can save CV information. 4. The system shows a prompt when no CV has been uploaded. | 3 | Used to store the applicant's CV materials. | 2026-03-22 | 2026-04-05
US3 | Search Available Jobs | As a TA applicant, I want to search for and view available jobs, so that I can find suitable positions to apply for. | Must | 2 | 1. The TA applicant can view current open jobs. 2. Each job shows basic information such as title, requirements, workload, and deadline. 3. The TA applicant can view job details. 4. The system shows a prompt when no jobs are available. | 5 | Supports applicants in viewing currently open jobs. | 2026-04-05 | 2026-04-19
US4 | Apply for Jobs | As a TA applicant, I want to apply for a job, so that I can be considered for the position. | Must | 3 | 1. The TA applicant can submit an application for a job. 2. The system records the application information. 3. The same applicant cannot apply for the same job more than once. 4. The system prevents submission when profile information is incomplete and explains the reason. | 5 | Used to submit job applications and record application information. | 2026-04-19 | 2026-05-03
US5 | View Application Status | As a TA applicant, I want to view my application status, so that I can understand the progress and result of each application. | Must | 1 | 1. The TA applicant can view their application records. 2. Each application record shows the related job. 3. Each application shows a status such as Pending, Accepted, or Rejected. 4. After the module organiser updates the status, the applicant can see the latest result. | 3 | Used to track application processing results. | 2026-03-22 | 2026-04-05
US6 | Post Jobs | As a Module Organiser, I want to post jobs, so that TA applicants can apply for them. | Must | 2 | 1. The module organiser can create a job posting. 2. The job includes information such as title, description, required skills, workload, and deadline. 3. The system can save the job information. 4. Posted jobs can be viewed by TA applicants. | 5 | Used to publish new teaching assistant job information. | 2026-04-05 | 2026-04-19
US7 | Select Applicants | As a Module Organiser, I want to review and select suitable applicants, so that I can complete the recruitment process. | Must | 4 | 1. The module organiser can view the list of applicants for a job. 2. The module organiser can view applicant profiles and CVs. 3. The module organiser can update the application status. 4. Updated application statuses are synchronised to the applicant side. | 8 | Used to review and process job applications. | 2026-05-03 | 2026-05-17
US8 | View Overall TA Workload | As an administrator, I want to view the overall workload of TAs, so that I can avoid overloading individual TAs. | Must | 4 | 1. The administrator can view the current workload of TAs. 2. The system shows overall workload information for each TA. 3. Workload information is linked to accepted or assigned jobs. 4. The administrator can identify TAs with excessive workload. | 5 | Used to help administrators balance TA work allocation. | 2026-05-03 | 2026-05-17